Rotary clubs generally follow a specific thought and planning process when writing projects. Below is a guide on how you can proceed step by step.

### 1. Needs Analysis and Idea Development

- Identifying Community Needs: It is crucial to understand the real needs of the targeted community. This can be accomplished through surveys, focus groups, interviews with local leaders, or by reviewing existing data. For example, a need such as lack of access to clean water in a specific region or children's inability to reach educational materials can be identified.

- Alignment with Rotary Areas of Focus: It is preferred that the project aligns with at least one of Rotary’s six main areas of focus (Promoting Peace; Fighting Disease; Providing Clean Water; Saving Mothers and Children; Supporting Education; Growing Local Economies). This ensures the project stands stronger in grant applications.

- Brainstorming: You can develop different approaches and solution proposals by brainstorming potential project ideas with club members.

### 2. Drafting the Project

- Project Title: Determine a memorable name that reflects the project's purpose.

- Problem Statement: Explain the problem the project intends to solve in a clear and concrete manner, identifying who is affected and how.

- Project Goal: State in a general expression what you aim to achieve (e.g., "Increasing access to clean water in the region").

- Project Objectives: Set specific, measurable, achievable, relevant, and time-bound (SMART) goals. For example: "Installing five new water pumps in X village within six months and providing clean water access to one thousand people".

- Target Audience: Define who will benefit from the project and the characteristics of this audience.

- Expected Results and Impacts: Explain the concrete outputs (results) and the long-term positive effects on the community.

  - Result: Installed water pumps, distributed educational materials.

  - Impact: Reduction in disease rates, increase in literacy levels.

### 3. Detailed Planning and Implementation

- Activities: List every step required to reach the project goals in chronological order. Examples include needs analysis, procurement of materials, training local labor, installing pumps, and organizing seminars.

- Timeline: Create a detailed timeline including start and end dates for each activity.

- Budget: Determine estimated costs item by item—including materials, labor, transportation, training, and promotion. Consider potential funding sources like club budgets, district funds, Rotary Foundation grants, partner clubs, or external sources.

- Resources: Identify necessary human resources (volunteers, experts), physical resources (equipment), and financial resources.

- Partnerships: Evaluate potential partnerships with other Rotary clubs, NGOs, local governments, or the private sector to expand the project's impact and resources.

### 4. Monitoring and Evaluation

- Monitoring Methods: Determine methods to track progress regularly (e.g., weekly meetings, progress reports, field visits).

- Evaluation Criteria: Define which indicators will be used to measure success and how they will be collected.

- Sustainability: Explain the mechanisms established to maintain the project's impact after completion, such as local training, transfer of maintenance responsibility, or cooperation with local authorities.

### 5. Risk Management

- Potential Risks: Identify possible issues such as funding problems, weather conditions, or lack of participation.

- Mitigation Strategies: Describe the measures and alternative plans to minimize or eliminate these identified risks.

### 6. Reporting and Communication

- Reporting: Plan for regular reporting on progress, results, and challenges to the club, district, and other stakeholders.

- Promotion: Specify how media, social media, or other communication channels will be used to announce the project's success and Rotary’s contribution.

### Project Title: "Strong Mothers for Healthy Generations" Rotary Project

1. Project Background / Problem Statement: In many areas, lack of access to health support during pregnancy, irregular prenatal check-ups, and lack of access to basic infant health services pose serious life risks. These issues are exacerbated in rural or low-income communities by lack of information, economic difficulties, and transportation issues. Local health center data shows that 40% of mothers in the region had fewer than three doctor visits during pregnancy, and 30% of infants did not receive their vaccines on time. This project is designed to provide both healthcare and awareness support.

2. General Goal: Contribute to a healthier and more conscious society by supporting maternal and child health.

3. Objectives (SMART):

- Provide prenatal and postnatal care training to at least 200 mothers in 6 months.

- Complete health screenings (vaccination, growth, nutrition) for at least 100 children.

- Train local health workers on early intervention and nutrition monitoring.

- Distribute mother-baby support packages (health kits, hygiene materials, brochures).

4. Target Audience: Pregnant or new mothers (18–40), infants (0–2), and family health center staff.

5. Project Activities:

- 1st Month: Needs analysis and collaboration with local health centers.

- 2nd Month: Preparation of health education content by volunteer doctors.

- 3rd–4th Month: Mother Education Days (3 sessions: Pregnancy, Nutrition, Vaccination).

- 4th–5th Month: Child health screenings.

- 5th Month: Distribution of care kits.

- 6th Month: Evaluation, reporting, and closing meeting.

6. Expected Results: Increased knowledge for mothers, ensured regular vaccination for infants, established permanent cooperation between health centers and Rotary, and an expected long-term decrease in maternal and infant mortality rates.

7. Budget (Sample):

- Total: 40,000 TL (Funded by club budget, partner contributions, and local sponsors).

8. Partners and Stakeholders: Local Rotary Club, Provincial Health Directorate, local family health centers, and volunteer healthcare professionals.

9. Risks and Precautions: Addressing low participation through local leaders, handling funding gaps through donation campaigns, and managing health obstacles like pandemics via hybrid training options.

10. Sustainability: Distributing educational materials digitally, forming an "Maternal Support Group," maintaining regular visit programs, and institutionalizing the annual "Mother-Baby Day" with the Provincial Health Directorate.